## DATA
PROJECT PIPELINE TRACKER |  |  |  |  | Visit indzara.com
[5 empty] | Password to unprotect: indzara |  |  |  |  | COMPLETED PROJECTS
| ENTER UP TO 6 STAGES |  |  |  | Please do not rename the STAGE DT fields
STAGE NAME
RESEARCH
APPROVAL
| DEVELOP | ACTIVE PIPELINE | [7 empty] | AVG. DURATION (DAYS)
TEST
EXECUTE
LAUNCH
ENTER PROJECTS |  |  | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH |  |  | Calculated | Calculated | Calculated | Calculated
PROJECT ID | NAME | START DATE | STAGE 1 DT | STAGE 2 DT | STAGE 3 DT | STAGE 4 DT | STAGE 5 DT | STAGE 6 DT | TYPE | OWNER | CURRENT STAGE | COMPLETION DATE | DURATION (DAYS) | VALIDATION
1 | Project One | 2016-05-01 | 2016-05-06 | 2016-05-06 | 2016-05-15 |  |  |  | Internal | Project Manager 1 |  |  |  | ERROR
2 | Project Two | 2016-05-05 | 2016-05-12 | 2016-05-13 | 2016-05-15 | 2016-05-18 | 2016-05-20 | 2016-05-21 | External | Project Manager 2 |  |  |  | ERROR
3 | Project Three | 2016-05-05: 2016-06-02; 2016-05-12: 2016-06-07 | Internal | Project Manager 1 |  |  |  | ERROR
4 | Project four | 2016-05-05: 2016-06-01; 2016-05-12: 2016-06-05 | External | Project Manager 1 |  |  |  | ERROR
5 | Project Five | 2016-05-05: 2016-06-02; 2016-05-13: 2016-06-05 | Internal | Project Manager 2 |  |  |  | ERROR
6 | Project Six | 2016-05-05: 2016-06-03; 2016-05-12: 2016-06-04; 2016-05-13: 2016-06-06 | External | Project Manager 1 |  |  |  | ERROR
7 | Project Seven | 2016-05-05: 2016-06-04; 2016-05-12: 2016-06-05; 2016-05-13: 2016-06-07; 2016-05-15: 2016-06-08 | Internal | Project Manager 1 |  |  |  | ERROR
8 | Project Eight | 2016-06-05 | 2016-06-08 | 2016-06-09 | 2016-06-11 | 2016-06-13 | 2016-06-15 |  | External | Project Manager 1 |  |  |  | ERROR
9 | Project Nine | 2016-06-05 | 2016-06-08 | 2016-06-09 | 2016-06-11 | 2016-06-13 | 2016-06-13 | 2016-06-13 | External | Project Manager 1 |  |  |  | ERROR
10 | Project Ten | 2016-06-05: 2016-06-06; 2016-06-08: 2016-06-08; 2016-06-09: 2016-06-09 |  |  | Project Manager 2 |  |  |  | ERROR
11 | Project Eleven | 2016-06-05: 2016-05-01 |  |  | Project Manager 3 |  |  |  | ERROR
12 | Project Twelve | 2016-04-01 | 2016-04-02 | 2016-04-03 | 2016-04-10 | 2016-04-20 | 2016-04-25 | 2016-04-28 | External | Project Manager 2 |  |  |  | ERROR
13 | Project Thirteen | 2016-03-01 | 2016-03-02 | 2016-03-08 | 2016-03-09 | 2016-03-12 | 2016-03-14 | 2016-03-20 | Intenal | Project Manager 1 |  |  |  | ERROR
14 | Project Fourteen | 2016-03-01 | 2016-03-02 | 2016-03-08 | 2016-03-09 | 2016-03-12 | 2016-03-14 | 2016-03-20 | Intenal | Project Manager 1 |  |  |  | ERROR
15 | Project Fifteen | 2016-03-01: 2016-06-02; 2016-03-02: 2016-06-05; 2016-03-08: 2016-06-08 | [5 empty] | ERROR
1
2
3
2
0
9
1
5
19

## ACTIVE PIPELINE
RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
Project Eleven | Project Three | Project Six | Project One |  | Project Eight
11 | 3 | 6 | 1 |  | 8
| Internal | External | Internal |  | External
Project Manager 3 | Project Manager 1 | Project Manager 1 | Project Manager 1 |  | Project Manager 1
| Project four | Project Ten | Project Seven
| 4 | 10 | 7
| External |  | Internal
| Project Manager 1 | Project Manager 2 | Project Manager 1
Project Fifteen
15
2
1
3
2
0
1

## REPORT
MONTHLY REPORT
Avg Duration in each Stage
|  | Projects Completed | Avg. Duration | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
| 2026-08-01 | 0
| 2026-07-01 | 0
| 2026-06-01 | 0
| 2026-05-01 | 0
| 2026-04-01 | 0
| 2026-03-01 | 0
| 2026-02-01 | 0
| 2026-01-01 | 0
| 2025-12-01 | 0
| 2025-11-01 | 0
| 2025-10-01 | 0
| 2025-09-01 | 0

## H (hidden)
STAGES
6 |  | Columns and Rows are designed to match the Active Pipeline sheet. Any insert or delete columns/rows will mess the formulas.
OPEN PROJECTS | 0
|  | MANUAL ENTRY | RESEARCH | APPROVAL | DEVELOP | TEST | EXECUTE | LAUNCH
STAGE | OPEN PROJECTS | 1
1 | 0 | 1
2 | 0 | 1
3 | 0 | 1
4 | 0
5 | 0 | 2
6 | 0 | 2
2
2
3
| AVG DURATION | 3
RESEARCH |  | 3
APPROVAL |  | 3
DEVELOP
TEST |  | 4
EXECUTE |  | 4
LAUNCH |  | 4
4
COMPLETED PROJECTS
0 |  | 5
5
TODAY |  | 5
2026-08-05 |  | 5
MIN PROJ START DATE
2016-03-01
AVG DURATIOn